## Sheet1
PES PROJECT - 5
UART Communications with PC
BY:AAKSHA JAYWANT AND RUCHA BORWANKAR
Sr.no | Potential Failure Mode | Potential Failure Effect | Severity (1-10) | Potential Cause | Occurrence (1-10) | Controls-How to prevent? | Detection (1-10) | Risk Priority Number
(Severity * Occurrence * Detection)
1 | Hardware error | No output received | 9 | Loose USB /static | 4 | Debugging using error detection and testing methods | 1 | 36
2 | Loss of data or code issue | Data loss or program wiped out | 10 | Security issue/erased data | 3 | Careful use of memory/allocating memory | 4 | 120
3 | Abnormal shutdown | No output received | 7 | PC error/System error | 3 | Check the system on which work is done | 2 | 42
4 | Overestimation of capacity | Segmentation fault | 10 | Wrong Memory estimation | 3 | Refer to the datasheet for memory specifications of the board | 7 | 210
5 | Delayed output | Slower responses to inputs | 6 | Print statements take time | 7 | Check the system on which one is working | 2 | 84
6 | Communication error | Microcontroller waits while PC keeps on giving instructions | 5 | Difference in baud rates | 8 | Set accurate baud rate according to the calculations | 1 | 40
Highest RPN=Overestimation of capacity=210
| References:- | "The highest RPNs should get highest priority for corrective measures."
https://polarion.plm.automation.siemens.com/hubfs/Docs/Guides_and_Manuals/Siemens-PLM-Polarion-How-to-conduct-a-failure-modes-and-effects-analysis-FMEA-wp-60071-A3.pdf
Goals of corrective measures include:
• Eliminate failure modes (some are more preventable than others)
• Minimize the severity of failure modes
• Reduce the occurrence of failure modes
• Improve detection of failure modes